## Slide 1: CHAPTER ONE OVER VIEW OF PROJECT LOGISTICS AND CONTRACT ADMINISTRATION

## Slide 2: Chapter Objectives :
At the end of this chapter, you will be able to:
Define logistics in general and project logistics in particular
Identify the inputs, methodology and outputs in the procurement management process
Understand the issues of contract administration, and
Its linkage to the procurement management process

## Slide 3: 1.1. Introduction to Project Logistics
Logistics is the function that enables the flow of materials from suppliers into an organization through operations within the organization out to the customers.
It is derived from the Greek word “logistikos” which means ‘to reason logically’
It is all operations required for goods (both tangible and intangible) to be made available in markets or at specific destinations.
According to Council of Logistic Management (USA)
“Logistics is the process of planning, implementing and controlling the efficient, effective flow and storage of goods, services and related information from the point of origin to the point of consumption for the purpose of conforming the customer requirements”.

## Slide 4
A logistics project can be defined as a complex, special and unique sets of activities which can be described by technical and economic parameters and is determined by cost, time, and scope in order to aid logistics management in enterprise/supply chain.
Controlling of the logistics project is process of measuring progress toward an objective, evaluating what remains to be done, and taking the necessary corrective tasks to achieve or exceed the objectives of the logistics project.
1.2. Logistics Activities
Logistics is responsible for the movement and storage of material as they move through the supply chain.
When the material is moving through an organization, one can see the following activities are normally included in logistics.

## Slide 5: 1.2. Logistics Activities
Key Activities | Support Activities
Customer service standards cooperate with marketing | Warehousing
Transportation | Material Handling
Inventory Management | Purchasing
Information flows and order processing | Protective packaging
 | Cooperate with production /operation/
 | Information maintenance

## Slide 6: 1.2. Logistics Activities

## Slide 7: 1.3. Project Procurement Management
Project Procurement Management includes the processes necessary to purchase or acquire products, services, or results needed from outside the project team to perform the work.
Figure: Project Procurement Management Processes and Key Outputs

## Slide 8: 1.3. Project Procurement Management
Project Procurement Management includes the contract management and change control processes required to develop and administer contracts or purchase orders issued by authorized project team members.
Project Procurement Management also includes administering any contract issued by an outside organization (the buyer) that is acquiring the project from the performing organization (the seller), and administering contractual obligations placed on the project team by the contract.

## Slide 9: Project Procurement Management processes:
Include the following:
1. Plan Procurements: The process of documenting project purchasing decisions, the approach, and identifying potential sellers.
2. Conduct Procurements: The process of obtaining seller responses, selecting a seller, and awarding a contract.
3. Administer Procurements: The process of managing procurement relationships, monitoring contract performance, and making changes and corrections as needed.
4. Close Procurements: The process of completing each project procurement.
These processes interact with each other and with the processes in the other Knowledge Areas.
Each process can involve effort from one or more persons or groups of persons, based on the requirements of the project.

## Slide 10
Each process occurs in one or more project phases, if the project is divided into phases.
Although the processes are presented here as discrete components with well-defined interfaces, in practice they overlap and interact in ways not detailed here.
The Project Procurement Management processes involve contracts that are:
Legal documents between a buyer and a seller.
A contract represents a mutually binding agreement that obligates the:
  Seller to provide the specified products, services, or results, and
  Buyer to provide monetary or other valuable consideration.

## Slide 11
A contract is a legal relationship subject to remedy in the courts.
The agreement can be simple or complex, and can reflect the simplicity or complexity of the deliverables and procured effort.
A procurement contract will include terms and conditions, and may incorporate other items that the buyer relies upon to establish what the seller is to perform or provide.
It is the project management team's responsibility to make certain that all procurements meet the specific needs of the project while adhering to organizational procurement policies.
Depending upon the application area, a contract can also be called for example, an agreement, an understanding, a subcontract, or a purchase order.

## Slide 12
Most organizations will have documented policies and procedures specifically defining the procurement rules and specifically prescribing who has delegated authority to sign and administer such agreements on behalf of the organization.
Although all project documents are subject to some form of review and approval, the legally binding nature of a contract usually means that it will be subjected to a more extensive approval process.
The primary focus of the review and approval process ensures that the contract language describes the products, services, or results that will satisfy the identified project need.
The project management team may seek support early from specialists in the disciplines of contracting, purchasing, law, and technical.
  Such involvement can be mandated by an organization's policies.

## Slide 13
The various activities involved in the Project Procurement Management processes form the life cycle of a contract.
By actively managing the contract life cycle and carefully wording the terms and conditions of the procurements, some identifiable project risks can be avoided or mitigated or transferred to a seller.
Entering into a contract for products or services is one method of allocating the responsibility for managing or sharing potential risks.
A complex project can involve managing multiple contracts or subcontracts simultaneously or in sequence.
  In such cases, each contract life cycle can end during any phase of the project life cycle.

## Slide 14
Project Procurement Management is discussed within the perspective of the buyer-seller relationship.
The buyer-seller relationship can exist at many levels on any one project, and between organizations internal to and external to the acquiring organization.
Depending on the application area, the seller can be called a contractor, subcontractor, vendor, service provider, or supplier.
Depending on the buyer's position in the project acquisition cycle, the buyer can be called a client, customer, prime contractor, contractor, acquiring organization, governmental agency, service requestor, or purchaser.
The seller can be viewed during the contract life cycle first as a bidder, then as the selected source, and then as the contracted supplier or vendor.

## Slide 15
The seller will typically manage the work as a project if the acquisition is not just for shelf material, goods, or common products.
In such cases:
The buyer becomes the customer, and is thus a key project stakeholder for the seller.
The seller's project management team is concerned with all the processes of project management, not just with those of this Knowledge Area.
Terms and conditions of the contract become key inputs to many of the seller's management processes.
The contract can actually contain the inputs (e.g., major deliverables, key milestones, cost objectives), or it can limit the project team's options (e.g., buyer approval of staffing decisions is often required on design projects).

## Slide 16
This process involves consideration of whether, how, what, how much, and when to acquire outside support.
When the project obtains products, services, and results required for project performance from outside the performing organization, the processes from Plan Procurements through Close Procurements are performed for each item to be acquired.
The Plan Procurements process also includes consideration of potential sellers, particularly if the buyer wishes to exercise some degree of influence or control over acquisition decisions.

## Slide 17
Consideration should also be given to who is responsible for obtaining or holding any relevant permits and professional licenses that may be required by legislation, regulation, or organizational policy in executing the project.
The requirements of the project schedule can significantly influence the strategy during the Plan Procurements process.
Decisions made in developing the procurement management plan can also influence the project schedule and are integrated with Develop Schedule, Estimate Activity Resources, and make-or-buy decisions.
The Plan Procurements process includes consideration of the risks involved with each make-or-buy decision, and also includes reviewing the type of contract planned to be used with respect to mitigating risks, sometimes transferring risks to the seller.

## Slide 18
PLAN PROCUREMENTS
A. Plan Procurements: Inputs
1. Scope Baseline
The scope baseline describes the need, justification, requirements, and current boundaries for the project.
It consists of the following components:
Scope statement.
The project scope statement contains:
  The product scope description,
  Service description and result description,
  The list of deliverables and acceptance criteria, as well as
  Important information regarding technical issues or concerns that could impact cost estimating.
  Examples of required constraints are delivery dates, available skilled resources, and organizational policies.

## Slide 19
b. Work breakdown structure (WBS).
The project's WBS provides a pictorial display of the relationships among the components of the project and the project deliverables.
c. WBS dictionary.
The WBS dictionary and related detailed statements of work provide an identification of the deliverables and a description of the work in each WBS component required to produce each deliverable.

## Slide 20
2. Stakeholder Requirements Documentation may include:
Important information about project requirements that is considered during planning for procurements.
Requirements with contractual and legal implications may include health, safety, security, performance, environmental, insurance, intellectual property rights, equal employment opportunity, licenses, and permits-all of which are considered when planning for procurements.
3. Teaming Agreements
Teaming agreements are a legal contractual agreement between two or more entities to form a partnership or joint venture, or some other arrangement as defined by the parties.
…Plan Procurements: Inputs

## Slide 21
… Teaming Agreements
The agreement defines buyer-seller roles for each party. Whenever the new business opportunity ends, the teaming agreement also ends.
Whenever a teaming agreement is in effect, the planning process for the project is significantly impacted.
Thus whenever a teaming agreement is in place on a project, the roles of buyer and seller are predetermined, and such issues as scope of work, competition requirements, and other critical issues are generally predefined in a teaming arrangement.
4. Risk Register
The risk register includes risk-related information such as the identified risks, risk owners, and risk responses.

## Slide 22
5. Risk-Related Contract Decisions
Includes agreements for insurance, bonding, services, and other items as appropriate, that are prepared to specify each party's responsibility for specific risks, should they occur.
6. Activity Resource Requirements:
Contains information on specific needs such as people, equipment, or location needs.
7. Project Schedule:
Contains information on required timelines or mandated deliverables dates.
8. Activity Cost Estimates:
Estimates are used as a basis on which to regard bids.

## Slide 23
10. Enterprise Environmental Factors: The enterprise environmental factors that can influence the Plan Procurements process include but are not limited to:
 Marketplace conditions, and
 Products services and results those are available in the marketplace, the supplier, past performance of suppliers, under what terms and conditions.
11. Organizational Process Assets: The Organizational process assets that influence the Plan Procurement process include but are not limited to:
 Formal procurement policies, procedures, and guidelines. Most organizations have formal procurement policies and buying organizations. When such procurement support is not available, then the project team will have to supply both the resources and the expertise to perform such procurement activities.
 Management systems that are considered in developing the procurement management plan and selecting the contract types to be used.
 Organizations will sometimes have an established multi-tier supplier system of pre-qualified sellers based on prior experience.
9. Cost Performance Baseline:
Provides detail on the planned budget over time.
10. Enterprise environmental factors:
The enterprise environmental factors that can influence the plan procurements process include but are not limited to:
  Marketplace conditions , and
  Products, services and results those are available in the marketplace,
  The supplier and past performance of suppliers,
  Under what terms and conditions.

## Slide 24
11. Organizational Process Assets: that influence the plan procurement process include but are not limited to:
Formal procurement policies, procedures, and guidelines. Most organizations have formal procurement policies and buying organizations.
When such procurement support is not available, then the project team will have to supply both the resources and the expertise to perform such procurement activities.
Management systems that are considered in developing the procurement plan and selecting the contract types to be used.
Organizations will sometimes have an established multi-tier supplier system of pre-qualified sellers based on prior experience.

## Slide 25
B. Plan Procurements: Tools and Techniques
1. Make-or-Buy Analysis
A make-or-buy analysis is a general management technique used to determine whether:
  A particular work can best be accomplished by the project team, or
  Must be purchased from outside sources.
Sometimes a capability may exist within the project organization, but may be committed to working on other projects.
  In this case the project may need to procure such effort from outside the organization in order to meet its schedule commitments.
Any budget constraints are factors which may influence make-or-buy decisions.

## Slide 26
If a buy decision is to be made, then a further decision of whether to purchase or lease is also made.
A make-or-buy analysis should consider all related costs; both direct costs as well as indirect support costs.
For example, the buy-side of the analysis includes both:
  The actual out-of-pocket costs to purchase the product, and
  The indirect costs of supporting the purchasing process.

## Slide 27
2. Expert Judgment
Expert technical judgment will often be used to assess the inputs to and outputs from this process.
Expert purchasing judgment can also be used to develop or modify the criteria that will be used to evaluate seller proposals.
Expert legal judgment may involve the services of legal staff to assist with unique procurement issues, terms, and conditions.
Such judgment, including business and technical expertise, can be applied to both the technical details of the procured products, services, or results and to various aspects of the procurement management processes.

## Slide 28
3. Contract Types
Although the firm-fixed-price type of contractual arrangement is typically the preferred type which is encouraged and often demanded by most organizations, there are times when another contract form may be in the best interests of the project when considering all factors.
If a contract type other than fixed-price is intended, it is incumbent on the project team to justify its use.
The type of contract to be used and the specific contract terms and conditions fix the degree of risk sharing being assumed by the buyer and seller.
All legal contractual relationships generally fall into one of two broad families, either fixed-price or cost reimbursable.
Also, there is a third hybrid-type commonly in use called the time and materials contract.
The more popular of the contract types in use are discussed below as discrete types, but in practice, it is not unusual to combine one or more types into a single procurement.

## Slide 29
Fixed-price contracts. This category of contracts involves setting a fixed total price for a defined product or services to be provided.
Fixed-price contracts may also incorporate financial incentives for achieving or exceeding selected project objectives, such as schedule delivery dates, cost and technical performance.
Sellers are legally obligated to complete such contracts, with possible financial damages if they do not.
Buyers must precisely specify the product or services being procured. Changes in scope can be accommodated, but generally at an increase in contract price.

## Slide 30
  Firm Fixed Price Contracts (FFP):
  The most commonly used contract type is the FFP.
  It is favored by most buying organizations because the price for goods is set at the outset, and not subject to change unless the scope of work changes.
  Any cost increase due to adverse performance is the responsibility of the seller, who is obligated to complete the effort.
  Under the FFP contract, the buyer must precisely specify the product or services to be procured, and any changes to the procurement specification can increase the costs to the buyer.

## Slide 31
  Fixed Price Incentive Fee Contracts (FPIF):
  This fixed-price arrangement gives the buyer and seller some flexibility in that it allows for deviation from performance, with financial incentives tied to achieving agreed to metrics.
  Typically such financial incentives are related to cost, schedule, or technical performance of the seller.
  Performance targets are established at the outset, and the final contract price is determined after completion of all work based on the seller's performance.
  Under FPIF contracts, a price ceiling is set, and all costs above the price ceiling are the responsibility of the seller, who is obligated to complete the work.

## Slide 32
  Fixed Price with Economic Price Adjustment Contracts (FP-EPA):
  This contract type is used whenever the seller's performance period spans a considerable period of years, as is desired with many long term relationships.
  It is a fixed-price contract, but with a special provision allowing for pre-defined final adjustments to the contract price due to changed conditions, such as inflation changes, or cost increases for specific commodities.
  The EPA clause must relate to some reliable financial index which is used to precisely adjust the final price.
  The FP-EPA contract is intended to protect both buyer and seller from external conditions beyond their control.

## Slide 33
Cost-reimbursable contracts:
This category of contract involves payments (cost reimbursements) to the seller for all legitimate actual costs incurred, plus a fee representing seller profit for completed work.
Cost-reimbursable contracts may also include financial incentive clauses whenever the seller exceeds, or falls below defined objectives, such as costs, schedule, or technical performance targets.
Three of the more common types of cost-reimbursable contracts in use are Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CFIF), and Cost Plus Award Fee (CFAF).
The cost reimbursable contract gives the project the needed flexibility to redirect a seller whenever the scope of work cannot be precisely defined at the start and needs to be altered, or when high risks may exist in the effort.

## Slide 34
  Cost Plus Fixed Fee Contracts (CPFF):
  Seller is reimbursed for all allowable costs for performing the contract work, and receives a fixed fee payment calculated as a percentage of the initial estimated project costs.
  Fee is paid only for completed work, and does not change due to seller performance. Fee amounts do not change unless the project scope changes.

## Slide 35: Cost Plus Incentive Fee Contracts (CPIF):
  Seller is reimbursed for all allowable costs for performing the contract work and receives a predetermined incentive fee, based upon achieving certain performance objectives as set forth in the contract.
  In CPIF contracts, if the final costs are less or greater than the original estimated costs, then both the buyer and seller share costs from the departures based upon a pre-negotiated cost sharing formula, e.g., an 80/20 split over/under target costs.

## Slide 36: Cost Plus Award Fee Contracts (CPAF):
  This is a cost reimbursement contract whereby the seller is reimbursed for all legitimate costs, but the majority of fee is only earned based on the satisfaction of certain broad subjective performance criteria, as defined and incorporated into the contract.
  The determination of fee is based solely on the subjective determination of seller performance by the buyer, and is generally not subject to appeals.

## Slide 37
Time and Material Contracts (T&M).
Time and material contracts are a hybrid type of contractual arrangement that contain aspects of both cost reimbursable and fixed-price type arrangements.
They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed.
These types of contracts resemble cost-reimbursable type arrangements in that they can be left open ended and may be subject to cost growth for the buyer.

## Slide 38
The full value of the agreement and the exact quantity of items to be delivered may not be defined by the buyer at the time of the contract award.
Thus, T&M contracts can increase in contract value as if they were cost reimbursable type arrangements.
Many organizations require not-to exceed values and time limits placed in all T&M contracts to prevent unlimited cost growth.
Conversely, T&M contracts can also resemble fixed unit price arrangements when certain parameters are specified in the contract.
Unit labor or material rates can be preset by the buyer and seller when both parties agree on the values for specific resource categories, for example senior engineers at so much per hour, or categories of materials at specified rates per unit.

## Slide 39
C. Plan Procurements: Outputs
1. Procurement Management Plan
The procurement management plan describes how the procurement processes will be managed from developing procurement documentation through contract closure.
The procurement management plan can include guidance for:
The types of contracts to be used;
Whether independent estimates will be used and if they are needed as evaluation criteria;
Those actions the project management team can take unilaterally, if the performing organization has a prescribed procurement, contracting, or purchasing department;

## Slide 40
Standardized procurement documents, if they are needed;
Managing multiple suppliers;
Coordinating procurement with other project aspects, such as scheduling and performance reporting;
Any constraints and assumptions that could affect planned procurements;
Handling the required lead times to purchase items from sellers and coordinating them with the project schedule development;

## Slide 41
Handling the make-or-buy decisions and linking them into the Estimate Activity Resource and Develop Schedule processes;
Setting the scheduled dates in each contract for the contract deliverables and coordinating with the schedule development and control processes;
A procurement management plan can be formal or informal, can be highly detailed or broadly framed, and is based upon the needs of each project.
The procurement management plan is a subsidiary component of the project management plan.

## Slide 42
Identifying requirements for performance bonds or insurance contracts to mitigate some forms of project risk;
Establishing the direction to be provided to the sellers on developing and maintaining a work breakdown structure (WBS);
Establishing the form and format to be used for the procurement/contract statements of work;
Identifying pre-qualified sellers, if any, to be used; and
Procurement metrics to be used to manage contracts and evaluate sellers.

## Slide 43
2. Procurement Statements of Work
Each procurement statement of work (SOW) defines for those items being purchased, only that portion of the project scope that is to be included within the related contract.
The SOW for each contract is developed from the project scope baseline. The procurement SOW describes the procurement item in sufficient detail to allow prospective sellers to determine if they are capable of providing the item.
Sufficient detail can vary, based on the nature of the item, the needs of the buyer, or the expected contract form.

## Slide 44
…Procurement Statements of Work
Procurement SOW describes the products, services, or results to be supplied by the seller.
Information included in a SOW can include specifications, quantity desired, quality levels, performance data, period of performance, work location, and other requirements.
The procurement SOW is written to be clear, complete, and concise.
It includes a description of any collateral services required, such as performance reporting or post-project operational support for the procured item.

## Slide 45
In some application areas, there are specific content and format requirements for a contract SOW. Each individual procurement item requires a SOW.
However, multiple products or services can be grouped as one procurement item within a single SOW.
The procurement SOW can be revised and refined as required as it moves through the procurement process until incorporated into a signed contract award.

## Slide 46
3. Make-or Buy Decisions
Make-or-buy documents the decisions of what project products, services, or results will be acquired from outside the project organization, or will be performed internally by the project team.
This may also include decisions to buy insurance policies or performance bond contracts to address some of the identified risks.
The make-or-buy decisions document can be as simple as a listing that includes a short justification for the decisions. These decisions can be altered as subsequent procurement activities indicate a requirement for a different approach.
4. Change Requests
Change requests to the project management plan, its subsidiary plans and other components may result from the Plan Procurements process.
Change requests are processed for review and disposition through the Perform Integrated Change Control process.

## Slide 47
5. Procurement Document Packages
Procurement documents are used to solicit proposals from prospective sellers.
Terms such as bid, tender, or quotation are generally used when the seller selection decision will be based on price (as when buying commercial or standard items), while a term such as proposal is generally used when other considerations, such as technical capability or technical approach are paramount.
Common terms are in use for different types of procurement documents and may include request for information (RFI), invitation for bid.
Request for proposal (RFP), request for quotation (RFQ), tender notice, invitation for negotiation, and contractor initial response. Specific procurement terminology used may vary by industry and location of the procurement.

## Slide 48
The buyer structures procurement documents to facilitate an accurate and complete response from each prospective seller and to facilitate easy evaluation of the responses.
These documents include a description of the desired form of the response, the relevant procurement statement of work (SOW) and any required contractual provisions.
With government contracting, some or all of the content and structure of procurement documentation can be defined by regulation.
The complexity and level of detail of the procurement documents should be consistent with the value of, and risks associated with, the planned procurement.
Procurement documents must be sufficient to ensure consistent, appropriate responses, but flexible enough to allow consideration of any seller suggestions for better ways to satisfy the same requirements.

## Slide 49
6. Source Selection Criteria
Selection criteria are often included as a part of the procurement solicitation documents.
Such criteria are developed and used to rate or score seller proposals, and can be objective or subjective.
Selection criteria can be limited to purchase price if the procurement item is readily available from a number of acceptable sellers.
Purchase price in this context includes both the cost of the item and all ancillary expenses such as delivery.
Other selection criteria can be identified and documented to support an assessment for a more complex product or service or results.

## Slide 50
Some examples of selection criteria are:
Understanding of need- How well does the seller's proposal address the procurement statement of work?
Overall or life-cycle cost- Will the selected seller produce the lowest total cost (purchase cost plus operating cost)?
Technical approach- Do the seller's proposed technical methodologies, techniques, solutions, and services meet the procurement documentation requirements or are they likely to provide more than the expected results?
Technical capability- Does the seller have, or can the seller be reasonably expected to acquire, the technical skills and knowledge needed?
Risk- How much risk is embedded in the statement of work, and how much risk will be assigned to the selected seller?

## Slide 51
…Some examples of selection criteria are:
Management approach- Does the seller have, or can the seller be reasonably expected to develop, management processes and procedures to ensure a successful project?
Warranty- at does the seller propose to warrant for the final product, and through what time period?
Financial capacity- Does the seller have, or can the seller reasonably be expected to obtain, the necessary financial resources?
Production capacity and interest- Does the seller have the capacity and interest to meet potential future requirements?
Business size and type- Does the seller's enterprise meet a specific type or category of business, such as small, women-owned, or disadvantaged small businesses, as defined by the buyer or established by governmental agency and set-forth as a condition of contract award?

## Slide 52
…Some examples of selection criteria are:
Past performance of sellers- at has been the past experience with selected sellers?
References- Can the seller provide references from prior customers verifying the seller's work experience and compliance with contractual requirements?
Intellectual property rights- Does the seller assert intellectual property rights in the work processes or services they will use or in the products they will produce for the project?
Proprietary rights- Does the seller assert proprietary rights in the work processes or services they will use or in the products they will produce for the project?

## Slide 53: II. CONDUCT PROCUREMENTS
Conduct Procurements is the process of obtaining seller responses, selecting a seller, and awarding a contract.
In this process the team will receive bids or proposals and will apply previously defined evaluation criteria, as applicable, to select one or more sellers who are both qualified to perform the work and acceptable as a seller?
Many factors can be evaluated in the seller selection decision process, for example:
Price or cost can be the primary determinant for a standard off-the-shelf item, but the lowest proposed price may not be the lowest cost if the seller proves unable to deliver the products, services, or results in a timely manner.

## Slide 54
Proposals are often separated into technical (approach) and commercial (price) sections, with each issue evaluated separately. Sometimes, management sections are required as a part of the proposal and also have to be evaluated separately.
Multiple sources could be required for critical products, services, and results to mitigate risks that can be associated with issues such as delivery schedules and quality requirements.
The potentially higher cost associated with such multiple sellers, including any loss of possible quantity discounts, and replacement and maintenance issues, are considered.

## Slide 55
The tools and techniques described here can be used alone or in combination to select sellers.
For example, a weighting system can be used to:
  Select a single seller that will be asked to sign a standard contract, and
  Establish a negotiating sequence by ranking all proposals by the weighed evaluation scores assigned to each proposal.
On major procurement items, the overall process of requesting responses from sellers and evaluating sellers' responses can be repeated.
A short list of qualified sellers can be established based on a preliminary proposal.
A more detailed evaluation can then be conducted based on specific and comprehensive requirements document requested from the sellers on the short list.

## Slide 56: A. Conduct Procurements: Inputs
1.Procurement Management Plan: The procurement management plan should describe how the remaining procurement processes (from solicitation planning through contract close-out) will be managed.
2.Procurement Document Package:
3.Source Selection Criteria: Source selection criteria can include information on the supplier's required capabilities, capacity, delivery dates, product cost, life-cycle cost, technical expertise, and the approach to the contract.
4.Qualified Sellers List:
5.Seller Proposals: Seller proposals prepared in response to a procurement document package form the basic set of information that will be used by an evaluation body to select one or more successful bidders (sellers).
6.Project Documents: To the extent that project documents are available, they are considered during the Select Sellers process.

## Slide 57: …Conduct Procurements: Inputs
7. Make or Buy Decisions:
8. Teaming Agreements:
Whenever a teaming agreement is in place, the buyer and seller roles will have already been decided by executive management.
In some cases the seller may already be working under some form of interim contract funded by the buyer or jointly by both parties.
The effort of the buyer and seller in this process is to collectively prepare a procurement statement of work and plan which satisfies the requirements of the project. The two parties will then negotiate a final contract for award.
9. Organizational Process Assets: Elements of the organizational process assets that can influence the Conduct Procurements process include but are not limited to:
Listings of prospective and previously qualified sellers, and
Information on relevant past experience with sellers, both good and bad.

## Slide 58: B. Conduct Procurements: Tools and Techniques
Bidder Conferences:
Bidder conferences (sometimes also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings with all prospective sellers and buyers prior to submittal of a bid or proposal.
They are used to ensure that all prospective sellers have a clear and common understanding of the procurement (both technical and contractual requirements), and that no bidders receive preferential treatment.
Responses to questions can be incorporated into the procurement documents as amendments.
To be fair buyers must take great care to ensure that all prospective sellers hear every question and answer from any individual seller.

## Slide 59
2. Proposal Evaluation Techniques:
On complex procurements, where source selection will be made based on seller responses to previously defined weighted criteria, a formal evaluation process will be defined by the buyer's procurement policies.
The evaluation committee will make their selection for approval by management prior to award.
3. Independent Estimates:
For many procurement items, the procuring organization may elect to either prepare its own independent estimate, or have an estimate of costs prepared by an outside professional estimator, to serve as a benchmark on proposed responses.
Significant differences in cost estimates can be an indication that the procurement statement of work was deficient, ambiguous, and/or that the prospective sellers either misunderstood or failed to respond fully to the procurement statement of work.
…Conduct Procurements: Tools and Techniques

## Slide 60: …Conduct Procurements: Tools and Techniques
4. Procurement Negotiations:
Negotiations clarify the structure and requirements of the purchases so that mutual agreement can be reached prior to signing the contract.
Final contract language reflects all agreements reached.
Subjects covered should include responsibilities and authorities, authority to make changes, applicable terms and governing law, technical and business management approaches, proprietary rights, contract financing, technical solution, overall schedule, payments, and price.
Contract negotiations conclude with a document that can be executed by both buyer and seller that constitutes the contract.

## Slide 61
For complex procurement items, contract negotiation can be an independent process with inputs (e.g., issues or an open items listing) and outputs (e.g., documented decisions) of its own.
For simple procurement items, the terms and conditions of the contract can be prefixed and non-negotiable, and only need to be accepted by the seller.
The project manager may not be the lead negotiator on procurements.
The project manager and other members of the project management team may be present during negotiations to provide assistance, and if needed to add clarifications of the project's technical, quality, and management requirements.

## Slide 62
5 Expert Judgment:
Expert judgment may be used in evaluating seller proposals.
The evaluation of proposals may be accomplished by a multidiscipline review team with expertise in each of the areas covered by the procurement documents and proposed contract.
This can include expertise from functional disciplines, such as contracting, law, finance, accounting, engineering, design, research, development, sales, and manufacturing.

## Slide 63
6 Advertising:
Existing lists of potential sellers can often be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications.
Some government jurisdictions require public advertising of certain types of procurement items; and most government jurisdictions require public advertising of pending government contracts.

## Slide 64
7. Internet Search:
The Internet has a major influence on most of the project procurements and supply chain acquisitions in organizations.
A vast majority of commodities, components, shelf-items can be quickly located and secured at a fixed-price on the Internet.
However, while the majority of purchased items may be obtained using the Internet, the high-risk, highly complex, procured effort that must be closely monitored cannot be obtained by this means.

## Slide 65
Conduct Procurements: Outputs
1. Selected Sellers:
The sellers selected are those sellers who have been judged to be in a competitive range based upon the outcome of the proposal or bid evaluation, and who have negotiated a draft contract, which will become the actual contract when an award is made.
Final approval of all complex, high-value, high-risk procurements will generally require organizational senior management approval prior to award.
2. Procurement Award:
A procurement contract is awarded to each selected seller. The contract can be in the form of simple purchase order, or a complex document.
Regardless of the document's complexity, a contract is a mutually binding legal agreement that obligates the seller to provide the specified products, services, or results, and obligates the buyer to compensate the seller.
A contract is a legal relationship subject to remedy in the courts.

## Slide 66
Resource Calendars: The quantity and availability of contracted resources and those dates on which each specific resource can be active or idle are documented.
Change Requests: Change request to the project management plan, its subsidiary plans and other components, such as the project schedule and procurement management plan, may result from the Select Sellers process. Requested changes are processed for review and disposition through the Perform Integrated Change Control process.

## Slide 67
3. Project Management Plan Updates: Elements of the Project Management Plan include but are not limited to:
4. Project Document Updates: Project documents that may be updated include but are not limited to:
Stakeholder requirements documentation,
Requirements Traceability Documentation, and
Risk Register.

## Slide 68: Administer Procurements
Administer Procurements is the process of managing procurement relationships, monitoring contract performance, and making changes and corrections as needed.
Both the buyer and the seller will administer the procurement contract for similar purposes.
Each must ensure that both parties meet their contractual obligations and that their own legal rights are protected.
The Administer Procurements process ensures that the seller's performance meets procurement requirements and that the buyer performs according to the terms of their legal contract.

## Slide 69
The legal nature of the contractual relationship makes it imperative that the project management team is aware of the legal implications of actions taken when administering any procurement.
On larger projects with multiple providers, a key aspect of contract administration is managing interfaces among the various providers.
Due to varying organizational structures, many organizations treat contract administration as an administrative function separate from the project organization.
While a procurement administrator may be on the project team, this individual typically reports to a supervisor from a different department. This is usually true if the performing organization is also the seller of the project to an external customer.

## Slide 70
Administer Procurements includes application of the appropriate project management processes to the contractual relationship(s), and integration of the outputs from these processes into overall management of the project.
This integration will often occur at multiple levels when there are multiple sellers and multiple products, services, or results involved.
The project management processes that are applied may include, but are not limited to:
    Direct and Manage Project Execution to authorize the contractor's work at the appropriate time;
Procurement administration also has a financial management component that involves monitoring of payments to the seller.
This ensures that payment terms defined within the contract are met and that seller compensation is linked to seller progress, as defined in the contract.

## Slide 71
One of the principal concerns when making payments to suppliers is that there be some close relationship of payments made to the work accomplished.
The Administer Procurements process reviews and documents how well a seller is performing or has performed based on the contract and established corrective actions when needed.
Also, the performance is documented as a basis for future relationships with the seller.
Seller performance evaluation by the buyer is primarily carried out to confirm the competency or lack of competency of the seller, relative to performing similar work on the project or other projects.

## Slide 72
Similar evaluations are also carried out when it is necessary to confirm that a seller is not meeting the seller's contractual obligations, and when the buyer contemplates corrective actions.
Administer Procurements includes managing any early terminations of the contracted work (for cause, convenience, or default) in accordance with the termination clause of the contract.
Contracts can be amended at any time prior to contract closure by mutual consent, in accordance with the change control terms of the contract.
Such amendments may not always be equally beneficial to both the seller and the buyer.

## Slide 73: Administer Procurements: Inputs
1. Procurement Documents
2. Procurement Management Plan.
3. Selected Sellers
4.Performance Reports: Seller performance-related documentation includes:
5. Approved Change Requests:
Approved change requests can include modifications to the terms and conditions of the contract, including the procurement statement of work, pricing, and description of the products, services, or results to be provided.
All changes are formally documented in writing and approved before being implemented.
6. Work Performance Data:
Work performance data , including the extent to which quality standards are being satisfied, what costs have been incurred or committed, which seller invoices have been paid, are all collected as part of project execution.

## Slide 74: Administer Procurements: Tools and Technique
1. Contract Change Control Systems:
A contract change control system defines the process by which the procurement can be modified.
It includes the paperwork, tracking systems, dispute resolution procedures, and approval levels necessary for authorizing changes.
The contract change control system is integrated with the integrated change control system.
2. Procurement Performance Reviews:
A procurement performance review is a structured review of the seller's progress to deliver project scope and quality, within cost and on schedule, as compared to the contract.
It can include a review of seller-prepared documentation and buyer inspections, as well as quality audits conducted during seller's execution of the work.

## Slide 75
3. Inspections and Audits:
Inspections and audits required by the buyer and supported by the seller as specified in the procurement contract, can be conducted during execution of the project to verify compliance in the seller's work processes or deliverables.
4. Performance Reporting:
Performance reporting provides management with information about how effectively the seller is achieving the contractual objectives.
5. Payment Systems:
Payments to the seller are typically processed by the accounts payable system of the buyer, after certification of satisfactory work by someone on the project team.
All payments should be made in strict accordance with the terms of the contract.

## Slide 76
6. Claims Administration:
Contested changes and potential constructive changes are those requested changes where the buyer and seller cannot reach an agreement on compensation for the change, or cannot agree that a change has even occurred.
These contested changes are variously called claims, disputes, or appeals. Claims are documented, processed, monitored, and managed throughout the contract life cycle, usually in accordance with the terms of the contract.
If the parties themselves do not resolve a claim, it may have to be handled in accordance with alternate disputes resolution (ADR) typically following procedures established in the contract.
Settlement of all claims and disputes through negotiation is the preferred method.

## Slide 77
7. Records Management System:
A records management system is a specific set of processes, related control functions, and automation tools that are consolidated and combined into a whole, as part of the project management information system.
A records management system is used by the project manager to manage contract and procurement documentation and records.
The system is used to maintain an index of contract documents and correspondence, and assist with retrieving and archiving that documentation.

## Slide 78
1. Procurement Documentation:
Procurement documentation includes but is not limited to the procurement contract with all supporting schedules, requested unapproved contract changes, and approved change requests.
Procurement documentation also includes any seller developed technical documentation and other work performance information, such as deliverables, seller performance reports, warranties, financial documents including invoices and payment records, and the results of contract-related inspections.
2. Organizational Process Assets Updates
Elements of the organizational process assets that may be updated include but are not limited to:
Correspondence
Payment schedules and requests
Seller performance evaluation documentation
Administer Procurements: Outputs

## Slide 79
Correspondence:
Contract terms and conditions often require written documentation of certain aspects of buyer/seller communications, such as the need for warnings of unsatisfactory performance and requests for contract changes or clarifications.
This can include the reported results of buyer audits and inspections that indicate weaknesses the seller needs to correct.
In addition to specific contract requirements for documentation, a complete and accurate written record of all written and oral contract communications, as well as actions taken and decisions made, are maintained by both parties.
Payment schedules and requests:
All payments should be made in accordance with the procurement contract terms and conditions.

## Slide 80
Seller performance evaluation documentation:
Seller performance evaluation documentation is prepared by the buyer.
Such performance evaluations document the seller's ability to continue to perform work on the current contract, indicate if the seller can be allowed to perform work on future projects, or rate how well the seller is performing the project work.
These documents can form the basis for early termination of the seller's contract, or determining how contract penalties, fees, or incentives are administered.
The results of these performance evaluations can also be included in the appropriate qualified seller lists.

## Slide 81
3. Change Requests:
Change requests to the project management plan, its subsidiary plans and other components, such as the project schedule and procurement management plan (Section, may result from the Administer Procurements process.
Change requests are processed for review and approval through the Perform Integrated Change Control process.
Requested changes can include direction provided by the buyer, or actions taken by the seller, that the other party considers a constructive change to the contract.
Since any of these constructive changes may be disputed by one party and can lead to a claim against the other party, such changes are uniquely identified and documented by project correspondence.

## Slide 82
4. Project Management Plan Updates:
Elements of the Project Management Plan that may be updated include but are not limited to:
5. Procurement management plan:
The procurement management plan is updated to reflect any approved change requests that affect procurement management, including impacts to costs or schedules.
6. Baseline schedule:
If there are slippages that impact overall project performance the baseline schedule may need to be updated to reflect the current expectations.

## Slide 83
Close Procurements
Close Procurements is the process of completing each project procurement.
It supports the Close Project or Phase process, since it involves verification that all work and deliverables were acceptable.
The Close Procurements process also involves administrative activities, such as updating records to reflect final results and archiving such information for future use.
Close Procurements addresses each contract applicable to the project or a project phase. In multi-phase projects, the term of a contract may only be applicable to a given phase of the project.

## Slide 84
In these cases, the Close Procurements process closes the procurement(s) applicable to that phase of the project.
Unresolved claims may be subject to litigation after closure.
The contract terms and conditions can prescribe specific procedures for contract closure.
Early termination of a contract is a special case of procurement closure, which can result from a mutual agreement of both parties, from the default of one of the parties, or for convenience of the buyer if provided for in the contract.

## Slide 85
The rights and responsibilities of the parties in the event of an early termination are contained in a terminations clause of the contract.
Based upon those procurement terms and conditions, the buyer may have the right to terminate the whole contract or a portion of the project, for cause or convenience, at any time.
However, based upon those contract terms and conditions, the buyer may have to compensate the seller for seller's preparations and for any completed and accepted work related to the terminated part of the contract.

## Slide 86
Close Procurements: Inputs
Procurement Management Plan
Procurement Documentation
Close Procurements: Tools and Techniques
1. Procurement Audits:
A procurement audit is a structured review of the procurement process originating from the Plan Procurements process through Administer Procurements.
The objective of a procurement audit is to identify successes and failures that warrant recognition in the preparation or administration of other procurement contracts on the project, or on other projects within the performing organization.

## Slide 87
2. Negotiated Settlements:
In all procurement relationships the fmal equitable settlement of all outstanding issues, claims, disputes, by negotiation is a primary goal of the project.
Whenever settlement cannot be achieved through direct negotiation, then some form of alternate disputes resolution (ADR) like mediation or arbitration may be explored.
When all else fails, litigation in the courts is the least desirable option.
3. Records Management System.
…Close Procurements: Tools and Techniques

## Slide 88
Organizational Process Assets Updates Elements of the organizational process assets that may be updated include but are not limited to:
Procurement file: A complete set of indexed contract documentation, including the closed contract, is prepared for inclusion with the final project files.
Deliverable acceptance: The buyer, usually through its authorized contract administrator, provides the seller with formal written notice that the deliverables have been accepted or rejected. Requirements for formal deliverable acceptance, and how to address non-conforming deliverables, are usually defined in the contract.
Lessons learned documentation: Lessons learned analysis, what has been experienced, and process improvement recommendations, should be developed for the project file to improve future procurements.
Closed Procurements:
The buyer, usually through its authorized procurement administrator, provides the seller with formal written notice that the contract has been completed.
Requirements for formal procurement closure are usually defined in the terms and conditions of the contract and are included in the procurement management plan.
Close Procurements: Outputs