## Slide 1
CONTRACTS AND
PAYMENT STRUCTURE
CHAPTER EIGHT

## Slide 2
8.1. Introduction
The nature of the contract between the purchaser and the contractor can take one of a variety of forms.
The nature of the contract depends on a range of issues, including the scope of the work, the responsibility of the contractor, the risk involved, and the urgency.

## Slide 3
8.2. CONTRACT STRUCTURES
When choosing to use contractors, the purchaser may follow one of several procurement routes, distinguished by the following features:
Responsibility for the design procurement
construction and commissioning is placed with one organization or is to be divided between several, separate organizations.

## Slide 4
There are several procurement routes commonly in use:
1. The traditional system: With the traditional method, the risks are divided between the Owner and the Contractor. where the design responsibility is primarily that of the architect or engineer employed by the client and the contractor or contractors are primarily responsible for construction only.

## Slide 5
2. The turnkey contract: where a single firm is employed by the client to undertake the design, procurement, construction, and commissioning of the entire works, including managing the process.

## Slide 6
3. The design and build contract: the contractor is responsible for design as well as construction.
The contractor’s detailed design is often developed from a conceptual design prepared by the client’s designers prior to tender.
The client’s design team is often seconded to work for the contractor after contract award.

## Slide 7
4. Construction management and management contracting:
The contractor is responsible only for the management of the contract, with all construction work done by others.

## Slide 8
5. Guaranteed maximum price: Combines construction management with design and build. The client and contractor agree on a maximum price for the project, with the contractor responsible for any costs above that amount.

## Slide 9
8.3. THE CONTRACT PRICE
There are 3 main ways in which the contract is calculated: 1. Lump sum. 2. Remeasurement, schedule of rates, or bill of quantities. 3. Cost reimbursement.

## Slide 10
On a single contract, the different ways may be combined. The choice of which way to price the work depends on the amount of information the purchaser can provide the contractor at the time of tendering, the conditions under which the work will be carried out, and the risk which it is sensible to expect the contractor to accept.

## Slide 11
LUMP SUM/ FIXED PRICE
From the purchaser’s financier viewpoint, the ideal is a firm lump sum with the minimum provisions for variations or claims. It establishes the amount of the commitment in advance, it provides the maximum incentive to the contractor to complete the work on time.
The purchaser must give complete and accurate information before a lump sum price can be produced.

## Slide 12
Con’t
Generally suitable where the project is well defined, and vital changes to requirements are not expected. This means that the contractor can perfectly price the works they are being asked to execute.
Features of Lump sum contract
Fixed budget (no extra cost)
Specified quality
Contractor’s risk

## Slide 13
Advantages
The client’s risk is minimal
Fewer variations
contractors have a clear expectation of the scope.
Disadvantages
Contractors’ risk is high
Budget constraints may limit project outcomes.
Improper details in the design can lead project disputes

## Slide 14
BILL OF QUANTITY
A bill of quantities is a document used in tendering in the construction industry in which materials, parts, and labor are itemized. It defines the quality and quantity of work required to be carried out by the contractor to complete a project.
These quantities are an accurate estimation of the work to be performed by the contractor except where any quantity is stated to be approximate.

## Slide 15
Con’t
If greater quantities of work are necessary to complete the works, then the contractor is entitled to be paid extra under the variations the clause in the contract.
It is the client who essentially bears the risk that the quantities are not an accurate estimation of the work, although the contractor takes the risk of an error in pricing.

## Slide 16
Advantages
The contractor’s risk is minimal
Valuing of variations orders
Disadvantages
The client’s risk is high
It increases the cost and design period in the pre-contract stage.

## Slide 17
COST REIMBURSEMENT
In some projects finishing by the earliest possible date is regarded as more important than obtaining the lowest capital cost.
Problem of CR paying the contractor the actual costs of carrying out the work provides no incentive for the contractor to minimize the costs.
many contractors do not like cost reimbursement because of the inefficiencies which it can raise within their own organizations.
There are various types of incentive or target cost contracts associated with cost reimbursement.

## Slide 18
Features contract forms
All these forms of contract have certain features in common:
1. The principle of design and construction being conducted in parallel rather than in series.
2. The tendering by the contractor of its fee inclusive of profit and overheads.
3. The recording of the actual costs which should exclude any costs associated with defective work or re-work to remedy defects.

## Slide 19
4.At the end of the contract the making of a comparison between the target and the actual costs
5.The sharing between the purchaser and the contractor of the difference between the adjusted target and the actual costs in proportions set out in the contract treatment of the contractor’s management fee.

## Slide 20
Difference’s in CR contract forms
(ICE 1995) provides for this to be a percentage of the actual cost and to be included within the comparison between target and actual cost.
In other forms the contractor’s fee is a lump sum and is not made part of the comparison.
the management fee is to be a lump sum

## Slide 21
Noted
As to the percentage sharing arrangements between the contractor and the employer, various alternatives are available. (arrangements should be kept as simple as possible).
The arrangements have two objectives:
To provide the contractor with a genuine incentive to complete the work for a cost below the target.
To protect the purchaser from the worst effects of a substantial cost overrun.

## Slide 22
Problems with target cost contracts
A. The setting of the target itself
Target must be realistic (not to be either beaten or exceeded by significant amounts).
Also not be far outside the normal limits of estimating accuracy.
However, the target cost form of the contract has been chosen because the uncertainties and risks involved in the contract do not allow the tendering of a lump sum price.

## Slide 23
B. Because of the risks and uncertainties, including those arising from the lack of design definition.
there is a real chance of substantial variations.
C. The use of a target cost contract imposes a substantial administrative and supervisory burden on the client in checking the contractor’s actual costs.

## Slide 24
TERMS OF PAYMENT
Terms of payment are typically associated with invoice payments. They are agreements that set expectations for payment when the client needs to pay you and the penalties for missing a payment.
Terms of payment are a matter on which the commercial, technical, and financial sides of the employer’s business may find themselves pulling in different directions.

## Slide 25
The employer may attain the best commercial and technical result if they offer the tenderers terms of payment with reasonable contractual safeguards .There are a number of advantages to this approach
1.The employer avoids having to restrict the tender list to large firms possessing the resources to finance the contract, whose overheads and prices are likely to be higher than those of smaller companies
2. It ensures that the tenderers do not have to inflate their tender prices by financing charges

## Slide 26
3. It gives encouragement to and allows the employer to take advantage of firms possessing technical initiative that would otherwise be held back from expanding by a lack of liquid cash.
4. The employer minimizes the risk of being saddled with a contractor who has insufficient cash with which to carry out the contract and of having therefore to either support the contractor financially or terminate the contract.

## Slide 27
There are also two other arguments that are often used to support the case for only paying at the end when the contract is complete.
1. Payment on completion provides the contractor with the best possible incentive to finish the whole of the work by the date for completion. It is far more effective than imposing liquidated damages for delay.

## Slide 28
2. Paying monthly as the work proceeds, as is normal in building and civil engineering contracts, has encouraged the establishment of small contractors who do not possess the technical and managerial competence to undertake the work, tender low, uneconomic prices, and lack the cash resources to fund the work when they run into difficulties.

## Slide 29
There is some truth in both these arguments, but the practice in the construction industry is too well established. It is recommended that payments should be related to the completion of milestones or activities. It is important to note that payment is only made for completed activities or, where they are grouped, against the completion of the group. There is no payment for a percentage complete.

## Slide 30
This method is suitable for building, mechanical, and electrical engineering and process plant contracts.
The possibility should always be considered of tying in payment with the completion of certain milestones which can be identified by the programmer.
The milestone could be, for example, the construction of a foundation for a particular item of mechanical plant.
Payment would then be made only against the completion of that item ready to receive the plant.

## Slide 31
Two problems particularly associated with a monthly payment of measurement contracts are the practice of contractors to over-measure during the early months of the contract and to front-end load by artificially increasing the rates for items of work carried out early.

## Slide 32
Delayed Payment
Delaying payment is a common thing.
Late payment is an act of breaking the agreement.
Contractors have the right to suspend the contract if payment is delayed.
If the contract doesn’t compensate for the wasted time, the commercial low allows the contractor to take 8% above the base rate.
This law is applicable to both small and large businesses.
Even if the law doesn’t state a specific period for delayed payment, one month above the due date is considered a late payment.

## Slide 33
Advanced Payment
It is recommended that advanced payments are avoided as much as possible.
If it’s must to pay in advance, it’s better if it’s secured by a bond.
If such payments have to be made for commercial reasons, then they should always be secured by a bond.

## Slide 34
This avoidance of advanced payment is applicable also to manufacturing plants.
If the manufacturer failed financially, recovering advanced payment is almost impossible.
If it becomes necessary to make such payments for commercial reasons, it should be identified and stated as the property of the purchaser.
Retention Money
It is better for the purchaser to retain a proportion of the contract price until the work has been completed.
Usually, it is up to 10%-20%.